## report1704978307602
Case Number | Severity | Case Record Type | EOL Grandfathered | Subject | Contact Name | Status | Case Owner | Latest External Update | Grade | Opened Date | Working Department | Comments(1/11/23) | SDN delivery Date | ETA for Testing | Comments(1/18/24) | Comments (1/24/24) | 2024-01-02 | 2024-02-08 | 2024-02-15 | 2024-02-22 | 2024-02-29 | 2024-03-07 | 2024-03-14 | 2024-03-21 | 28th march | 4th april | 11th April | 18th April | 25th April | 2024-05-02 | 20th June | Follow on Call
7647156 | Low | Client Case | 0 | Incorrect user shown in Activity Tracking/Audit screen for manifest transaction | Animesh Mahato | MA-Researching | Nived Ashok | 12/13/23 2:39 EST (NA): The issue replicated in client environment. The Logs and replication document has been attached in the WR. Need to be picked by technical team | 25 | 2023-10-05 | CSO | Under Research |  |  | Research and Techncial analysis in Progress | Technical analysis in Progress. | Not able to get any findings from the logs. Analysis in Progress | Need a test data from Cristobal. Have sent mail | Will connect with Cristobal | Meeting to be scheduled today | Meeting to be scheduled today at 11.30 AM EST | Call will be initiated today | Call not yet initiated as I was on leave this week. Will initiate the same on 18/03/24 | will be done along with P-0027 issue | logs collected. Under technical analysis | logs collected. Under technical analysis | logs collected. Under technical analysis | logs collected. Under technical analysis | logs collected. Under technical analysis | logs collected. Under technical analysis | 20 June : Technical team is reviewing 13 June - Collected the new logs 06 June -Cris confirmed that he will set up a call to collect the logs again 30-May : Cris confirmed that he will set up a call to collect the logs again 23 - May - Logs collected. Under Technical Analysis 16- May -Logs collected. Under Technical Analysis 05- May - Logs collected. Under technical Analysis | Tony to Discuss
7864072 | Medium | Client Case | 0 | UOM Qty issues after P-0026 is applied | Nived Ashok | WC-Delivered | Nived Ashok | 1/8/24 3:57 EST (NA): Tech team is yet to deliver the Fix for this after the earlier SDN failed in client environment | 39 | 30/6/2023 | CSO | SDN will be delivered tomorrow |  | 2023-01-17 | SDN Delivered | SDN-P-0043 Delivered to fix the Issues related to P-0026 | Waiting for feedback after testing | Waiting for feedback after testing | Waiting for feedback after testing | Waiting for feedback after testing | Waiting for feedback after testing | Waiting for feedback after testing | Waiting for feedback after testing | 1 Open issue of UOM qty exist. Working session initiated for replicating label issue | Issue fixed in our local environment. Demo will be scheduled | Issue fixed in our local environment. Demo will be scheduled | Issue Fixed. Demo done. SDN will be delivered on 14/04/24 | SDN-P-0050 Delivered | SDN-P-0050 Delivered | SDN-P-0050 Delivered | 20 June: SDN-P-0050 Delivered 13-June - SDN-P-0050 Delivered 06 June - SDN-P-0050 30-May - SDN-P-0050 Delivered 23-May - SDN-P-0050 Delivered 16- May - SDN-P-0050 Delivered 05 - May - SDN-P-0050 Delivered | Boeing teams owns.
7908316 | High | Extension/Services | 0 | iLPN label missing the lot number for XO receiving | Sivakumar Jeevarathinam | WC-Delivered | Nived Ashok | 10/12/23 6:54 EST (NA): A HLE sent to client and waiting for approval | 47 | 2023-09-08 | CSO | Tony to send an update |  |  | Approval Received. Development will start | Will confrim once the development starts | Development started. ETA - 19/02/24 | Development completed. | Developmnet completed. SDN will be delivered after P-0047 is Installed | Development completed. SDN will be delivered after P-0047 is Installed | Development completed. SDN will be delivered after P-0047 is Installed | SDN-P-0049 Delivered | SDN-P-0049 Delivered | Configuration document sent. Working fine | Working fine | Working fine | Working fine | Working fine | Working fine | Working fine | 20 June : Working fine 13-June - Working FIne 06 June - Working fine 30 May - Working fine 23 May - Working fine 16 May - Working fine 05 May - Working fine | Boeing teams owns.
7871652 | High | Extension/Services | 0 | Batch#2021LMK1RT fails in WMS for Vergiate Site | Sivakumar Jeevarathinam | WC-Delivered | Nived Ashok | 10/27/23 7:37 EST (NA): Estimate provided to client and waiting for approval | 56 | 2023-07-07 | CSO | Estimate sent on 10/26/23. Waiting for approval |  |  | Approval Received. Development will start | A Mail has been sent briefing about the requirement. Need an Approval for the mail before we start the developmentAs ther eis no Mod spec available here | Development started. ETA - 07/02/24 | Development completed. | SDN P-0047 Full Build Delivered | SDN P-0047 Full Build Delivered | SDN P-0047 Full Build Delivered | SDN P-0047 Full Build Delivered | SDN P-0047 Full Build Delivered | Working fine | Working fine | Working fine | Working fine | Working fine | Working fine | Working fine | 20 June : working fine 06 June - Working fine 30 May - Working fine 23 May - Working fine 16 May - Working fine 05 May - Working fine | Boeing teams owns.
7814512 | Low | Extension/Services | 0 | WMOS Adjustment approval (Miami Ops) - *Prioritize* | Animesh Mahato | WC-Delivered | Nived Ashok | 12/10/2023 - BDSI_2017_PHASE4_SDN-P-0039 delivered. | 21 | 14/6/2023 | CSO | SDN Delivered. | 2023-10-12 |  | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | P-0042 / Cristobal.
7713894 | Low | Client Case | 0 | Overbag Labels Field Mapping/Configuration | Anuja Kumar Behera | WC-Delivered | Nived Ashok | 4/8/2023 - BDSI_2017_PHASE4_SDN-P-0032 delivered. | 23 | 24/5/2023 | CSO | SDN Delivered. | 2023-07-27 |  | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | P-0042 / Cristobal.
7647878 | Low | Client Case | 0 | CURE DATE & SHELF DATE on Overbag Label - Help | Garcia Labastida | WC-Delivered | Nived Ashok | 4/8/2023 - BDSI_2017_PHASE4_SDN-P-0032 delivered. | 25 | 2023-10-05 | CSO | SDN Delivered. | 2023-07-27 |  | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | P-0042 / Cristobal.
7776506 | Medium | Extension/Services | 0 | MIAMI:SHM0442064 Batch is Held | Sivakumar Jeevarathinam | WC-Delivered | Nived Ashok | 13/9/2023 - BDSI_2017_PHASE4_SDN-P-0036 delivered. | 44 | 2023-06-06 | CSO | SDN Delivered. | 2023-09-13 |  | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | P-0042 / Cristobal.
8265101 | High | Client Case | 0 | Issues related to P-0027 ( Bag/content label not printing ) | Nived Ashok | WC-Delivered | Nived Ashok | 3/1/2024 - BDSI_2017_PHASE4_SDN-P-0042 delivered. | 0 | 2023-05-12 | CSO | Will be investigated after P-0026 related issues are fixed with the delivery of our next SDN. |  |  | Will be investigated after P-0026 related issues are fixed with the delivery of our next SDN. | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Waiting for client to Test P-0026 and come back with the original issue details of P-0027 | Working session for label issue to be initiated for tomorrow | Issue replicated in our local environment. Fix in progress | Demo will be scheduled tomorrow | Demo over. 2 new Issues/CR's identified. Will sent the estimate for the same. New SDN with the fixes of label printing will be delivered on 14/04/24 | SDN-P-0050 Delivered | SDN-P-0050 Delivered | SDN-P-0050 Delivered | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN dleivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | Boeing teams owns.
7859807 | High | Extension/Services | 0 | EX77 Wave Template allocating Partial Order quantity | Sivakumar Jeevarathinam | WC-Delivered | Nived Ashok | 4/10/2023 - BDSI_2017_PHASE4_SDN-P-0035 delivered. | 59 | 28/6/2023 | CSO | SDN Delivered. | 2023-08-16 |  | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | SDN Delivered. | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN delivered 16 May - SDN Delivered 05 May - SDN delivered | Boeing teams owns.
8321038 | High | Client Case |  | EX52:RFID Serial labels not printing for multiple controls allocation |  | WC-Need Info | Shagun | [9 empty] | A meeting to be scheduled for a working session | Issue cannot be replicated in local…Have connected with boeing team on a working session and collected logs from client env | Issue cannot be replicated in local…Have connected with boeing team on a working session and collected logs from client env | Issue cannot be replicated in local…Have connected with boeing team on a working session and collected logs from client env | we requre java outbound logs from client environment. Also need a working session along with our technical team | Logs collected. | Logs collected and technical analysis in progress | The Actual issue fixed. Warning message is not gettign displayed. Mail sent to client to get steps on hpw to proceed in local | Need to connect with PSO team | Need to connect with PSO team | The issue resolved in our local env. Checking the client env for all the configs | Issue now found only when there are 2 control numbers. Need to analyze | Analysis in progress | It is working for 2 control numbers also in our local env | 20 June - Need to set up a call 13 June - Need to set up a call to cpnclude on this 06 June - Call was scheduled with Siva 30 May - More data sets requested 23 May - Awaiting feedback from client 16 May - It is working for 2 control numbers also in our local env 05 May - It is working for all data except one data | Cristobal -- Will speak with Anuja regarding: 8464956: Need to add some visibility for serial label prints
8317532 | High | Client Case |  | WMS M- Cycle Count Physical Prompt Issue |  | WC-Delivered | Nived Ashok | [9 empty] | Issue replicated. | Issue replicated. Techncial team working on giving a HLE to fix the issue. Will be provided by 12/2/24 | HLE shared with client. Waiting for approval | HLE shared with client. Waiting for approval | HLE shared with client. Waiting for approval | HLE shared with client. Waiting for approval | HLE shared with client. Waiting for approval | Approval Received. Development started | Issue Fixed. Testing in Progress | Demo to be scheduled tomorrow if team available | Demo Over. Working fine. SDN will be delivered on Monday | SDN P-0051 Delivered | SDN P-0051 Delivered | SDN P-0051 Delivered | 20 June - SDN-P-0051 Delivered 13 June - SDN-P-0051 Delivered 06 June - SDN-P-0051 Delivered 30 May - SDN-P-0051 delivered 23 May - SDN-P-0051 Delivered 16 May - SDN-P-0051 Delivered 05 May- SDN-P-0051 Delivered | Cristobal to get details.
8425560 | High | Client Case |  | P-0027 Changes - VAS/NON VAS determination for Qty prompt and overbag label printing |  | WC-Need Approval | Nived Ashok | [19 empty] | New case created to track the changes in P-27 | Estimate shared . Waiting for approval | Estimate shared . Waiting for approval | Estimate shared . Waiting for approval | 20 June - Yet to set up a working session. Found out few issues after the fix is ported from PSO env 13 June - All the Issues are fixed. Will set up a working session to jointly test. Please confirm the time 06 June - PSO has fixed the Issues . Will set up a working session to review the changes 30 May - PSO is reviewing 23 May - Estimate Shared. Waiting for Approval 16 May - Estimate Shared. Waiting for Approval 05 May - Estimate shared. Waiting for aPproval | Cris/Tony
8418861 | High | Client Case |  | KLXA ¦¦ EX01:Control number reset in Next up number |  | WC-Need Info | Nived Ashok | [19 empty] | Under Replication process | Call to be scheduled | Mail sent. Waiting for details | Siva confirmed that the script is part of SDN. Waiting for more details | 20 June : Siva to confirm 23 May - Siva confirmed that the script is part of SDN. Waiting for more details 16 May - Siva confirmed that the script is part of SDN. Waiting for more details 05 May - Siva confirmed that the script is part of SDN. Waiting for more details | Siva. Discussed with Sandeep. Wants to set up as DB cron job. Ask MA to close.
8420354 | High | Client Case |  | Storge Temp is incorrect value |  | Wc-Need Approval | Nived Ashok | [19 empty] | Under Research | Issue replicated. Under technical analysis to determine the HLE | Estimate will be sent before today E0D | Estimate Sent. Waiting for approval | 20 June : Signed SOW received. Development will be planned 13 June - Approval Received. SOW pending 06 June - Awaiting approval 30 May - Awaiting approval 23 May - HLE shared. Waiting for approval 16 May - HLE shared. Waiting for approval 05 May - HLE shared. Waiting for approval | Pending Delivery date from MA. Cris/Eddie.
8425882 | High | Client Case |  | RF Receiving transaction not flowing as expected |  | WC-Need Approval | Nived Ashok | [19 empty] | Under Research | Under Research | Call to be scheduled for Monday | Call to be scheduled | 20 June : 20 June : Signed SOW received. Development will be planned 13 June - Need to decide on the future steps 30 May - Findings will be shared today 23 May - HLE shared. Waiting for approval 16 May - Estimation in Progress 05 May - Call to be scheduled | Pending Delivery date from MA. Cris/Eddie.
8437836 | High | Client Case |  | EX77: Changes in Store procedure - SP change |  | WC-Delivered | [23 empty] | SDN will be delivered tomorrow | 20 June - SDN delivered 13 June - SDN delivered 06 June - SDN delivered 30 May - SDN delivered 23 May - SDN Delivered 16 May - SDN delivered | Cris. P-0052 EX77 - MSP Fix for 0 or no MSP
8454298 | High | Extension/Services |  | Cycle Count - Nextup Physical Count Prompt based on User |  | WC-Need Info | [24 empty] | 23 May : Estimation in Progress 16 May - Estimation in Progress 05 May - Call to be scheduled | Cris/Eddie. to review response.
8464956 | High | Extension/Services |  | Need to add some visibility for serial label prints |  | WC-Need Approval | [24 empty] | 20 June : Anusha will be seting up call with cris 13 June - Anusha is reviewing and will revert 30 May - Re estimation in progress 23 May - Estimation in progress 16 May - Estimation in progress | Cristobal -- Will speak with Anuja regarding: 8464956: Need to add some visibility for serial label prints
8460449 | High | Extension/Services |  | Changes to EX77 Logic to work with Packaging Requirements in EA Orders |  | WC- Need Approval | [24 empty] | 20 june : HLE sent for approval 13 June - HLE sent for approval 06 June- HLE will be sent today for approval 30 May - Requirements are clear. Estimation in progress 23 May - Call scheduled to discuss the requirement 16 May - Research in progress | Pending Delivery date from MA. Cris/Eddie.
8471350 | High | Extension/Services |  | Henkel Static Substitution Changes - REMLIFE/EXPDATE - CHG0066273 |  | WC-Need Approval | [24 empty] | 20 June : Signed Sow received 13 June - SOW pending 06 June : HLE is sent for approval 30 May - Requirements are clear. HLE will be sent tomorrow 23 May - Call scheduled to discuss the requirement | P-0042 / Cristobal.
8485938 |  | Extension/Services |  | Transitional Inventory - Cancelled Orders (EX 67 code from BEN Source Branch) |  | MA-Researching | [24 empty] | 20 June : Technical analysis in progress 06 June : Under Research | Tony/Cris to Discuss
8485856 |  | Extension/Services |  | Re-Putaway after Picking/Pull Process |  | MA-Researching | [24 empty] | 20 June : Under Research 06 June : Under Research | Tony to Discuss
8501519 |  | Extension/Services |  | EX66 SSO with Boeing IDP (RSA) added to P-Series SDN Branch |  | MA-Researching | [24 empty] | 20 June : Under research 13 June: Under Research | Cris to Discuss Request for info on scanner login.
8471917 |  | Extension/Services |  | SAAA Label not printing barcode for lot number for UOM LB |  | MA- Estimating | [24 empty] | 20 June : HLE will be sent today | Cris to look for HLE and see progress.
8504561 |  | Extension/Services |  | COFE/WMS Cubby Prioritization Interface | [26 empty] | 20 June : Yet to pick up | Tony/Eddie

## Sheet7
Case Number | Case Record Type | Subject | Contact Name | Status | Case Owner | Opened Date | Remarks
7938540 | Client Case | COP UAT:EX50 not working as per design | Sivakumar Jeevarathinam | WC-Need Approval | Nived Ashok | 2023-05-09 | The HLE was shared on 10/26/23. Can we close the case if we are not proceeding with this change ? | can be closed
7092348 | Extension/Services | INC0689297 - WMS “EPI Manifest” program (EX11) issue for HAZMAT item shipment, incorrect data has been sent to FedEx thru ProShip | Yongjian Gao | WC-On Hold | Nived Ashok | 21/12/2022 | The HLE was shared on 09/18/23. Can we close the case if we are not proceeding with this change ? | can be closed
7963459 | Extension/Services | WMS DO screen changes & Cancellation reason code | Sivakumar Jeevarathinam | WC-Need Approval | Nived Ashok | 15/9/2023 | The HLE was shared on 02/01/24. Can we close the case if we are not proceeding with this change ? | can be closed
7256462 | Client Case | Wichita / Invalid Task Group using VWC post deployment of P-0017/P-0018 | Matthew Miller | WC-Need Info | Nived Ashok | 22/2/2023 | Is this issue still exist and what is the Business impact ? Can we close the case if there is no impact. If it is a priority can we schedule a session to discuss on this | need to research
7073684 | Client Case | KLXA - Issue with task skipping in Burgess hill | Animesh Mahato | MA-Technical Analysis | Nived Ashok | 2022-12-12 | Is this issue still exist and what is the Business impact ? Can we close the case if there is no impact. If it is a priority can we schedule a session to discuss on this | can be closed
8390763 | RCA | RCA for 8390593 - WMS Henstedt HEN_BDS_PROD_22 is down due to high memory utilization | Jeevakumar G | WC-Need Info | Nived Ashok | 14/3/2024 | No Action required from MA. Can we close the case ? | can be closed